## Iter1
SE-1707 Evaluation for Iteration |  |  | Group 4
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Login with Google |  | Allow users to login with Google via the Login with google button. Default user is Customer, E-mail will be saved DB for next login. If E-mail is available in the DB, the user will be logged in with the old credentials | TungLD | Done
2 | Login with Username and Password |  | Allow user to login with Username/E-mail and Password | TungLD | Done
3 | Pagination, blocking access from url |  | Paging for User, blocking access to the page via the URL if not logged in or logged in but not in the correct role |  | Done
4 | Build Template for Client, Mentor, Admin |  | Create FE for admin site, mentor site, client site, display necessary information for each screen | KienNT | Done
5 | Regiter |  | Allow users to register with all necessary information. Check the exception of the input. Registering for the role of mentor and customer must add both data to 2 tables User and Mentor or Customer respectively | KienNT | Done
6 | Forgot password |  | Forgot Password will send the user a code that lasts for 30 seconds if the e-mail entered is in the DB. Entering the correct code and new password will change the user's password. Check exception for new password | TungLD | Done
7 | Show List Mentor in home page |  | Push the necessary data to the Home page (mentor is displayed as a mentor that is not blocked by admin) | KienNT | Done
8 | Show List Course in Home page |  | Push the necessary data to the Home page (Course is displayed as a mentor that is not blocked by admin) | DucPM | Done
9 | Change Status User |  | Change the user status (block, unblock) if the user is blocked, they will not allow access to the system. | MaiPHN | Done
10 | Update Profile User |  | Allows to change the necessary information on the Profile page. When you click Save, the new data will be saved to the DB and displayed at the same time | KienNH | Done
11 | Show List Course in MentorSite and AdminSite |  | Push the necessary data to the page | DucPM | Done
12 | Add new Course by mentor |  | Allow Mentor add new Course in Mentor Site | KienNT | Done
13 | Add new Course Type by Admin |  | Allow Admin add new Type in Admin Site | KienNH | Done
14 | Add news to the systems |  | Allow mentor add new News to the System | MaiPHN | Done
Note on G4: KienNT: The name of section in the SRS (software requirement specification) document
Note on H4: KienNT: The name of section in the SDS (software design specification) document

## iter2
SE-1707 Evaluation for Iteration |  |  | Group 4
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | List Course By Type |  | Show Course by Type | KienNT
2 | News |  | Show all news and News details. Internal News + Promotion news | MaiPHN
3 | List Course Enrolled |  | list of registered courses of respective users | KienNT + KienNH
4 | List Mentor |  | Show Mentor, mentor details and course by mentor | KienNT
5 | Online Payment |  | Embed Online payment method into system | TungLD
6 | Live BoxChat |  | Embed Online chat box method into system | TungLD
7 | Add Module Course |  | When add course, allow mentor all more module | DucPM + KienNT
8 | Smart Search Bar |  | Auto-suggest according to the keyword entered in the search bar | KienNT
9 | Default Payment |  | Create Modal to show pay detail when click "Enroll this course" button | KienNT + KienNH
Note on G4: KienNT: The name of section in the SRS (software requirement specification) document
Note on H4: KienNT: The name of section in the SDS (software design specification) document

## Iter3
SE-1707 Evaluation for Iteration |  |  | Group 4
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Handle URL |  | Handle URL of all page | KienNT
2 | Flash card page |  | Allow mentor add more flash card to learn | KieNH
3 | Embed Analytics tool |  | Embed Analytics tool to the project | KienNT
4 | Update News |  | Create page to update News | MaiPNH
| Embed Live box chat |  | Embed live box chat to the web | TungLD
5 | CRUD News type |  |  | DucPM
Note on G4: KienNT: The name of section in the SRS (software requirement specification) document
Note on H4: KienNT: The name of section in the SDS (software design specification) document